## Sheet1
Bug ID | Priority | Title | Overview | Steps to Reproduce | Expected Behavior | Actual Behavior | Screenshots
Bug_1 | High | Search Functionality Issue: Course Not Found with Similar Name | When searching for a course with the name "chatgpd," the expected result is to find the course "chargpt," but the course is not displayed in the search results. | 1. Log in as an admin 2.Go to the link :http://localhost/wordpress/wp-admin/admin.php?page=academy-courses&action=new 3.Create a new course with the name "chatgpt" 4.Go to the link: http://localhost/wordpress/index.php/courses/ 4.write "chatgpd" in search form | The course "chatgpt" should be displayed in the search results since the search term is similar. | The course "chatgpt" is not shown in the search results when using the term "chatgpd." | url: https://drive.google.com/file/d/1gTuMg3WA-uO_6RfskICro85IswgrDaaz/view?usp=drivesdk
Bug_2 | Medium | Duplicate Course Name Allowed During Creation | Despite having a course with the same name existing in the system, a new course with an identical name ("ChatGPT") is allowed to be created. | 1.Log in as an admin. 2.Go to the link:http://localhost/wordpress/wp-admin/admin.php?page=academy-courses&action=edit&id=21 3.Create a new course with the name "ChatGPT." 4.Go to the link: http://localhost/wordpress/wp-admin/admin.php?page=academy-courses&action=edit&id=21 5.Create a new course with the name "ChatGPT." 6.Go to the link: http://localhost/wordpress/wp-admin/admin.php?page=academy-courses | The system should prevent the creation of a course with a duplicate name and provide a relevant error message. | A new course with the name "ChatGPT" is created, despite an existing course with the same name. | url: https://drive.google.com/file/d/1mZLpp3luwYBedk6lg70LHCMX5nk1YodP/view?usp=sharing
Bug_3 | High | Timezone Display Discrepancy | After changing the WordPress timezone setting to Dhaka, the course creation time is still displayed in the previous America time zone, causing a discrepancy. | 1.Log in as an admin. 2.Go to WordPress settings and change the timezone to America. 3.Create a new course. 4.Note down the time 4.Go to WordPress settings and change the timezone to Dhaka | The course creation time should be displayed in the updated Dhaka timezone after changing the WordPress timezone setting. | The course creation time is still displayed in the previous America time zone. | url: https://drive.google.com/file/d/161xhJRBPPN0myJO51XqZ7QUcgc10ypZZ/view?usp=sharing